## Sheet1
Date | Description | Was it working before? | Who is working on it | Date completed | Notes
Since module was installed | Authorize.net double charging issue | No | Saurav / Sagar / Ajeet | 2014-08-01 | No longer double charging - started new issue of charging $0.01 on all declined transactions.
Since June | Shipping error - 'None Type' object has no attribute 'weight_net' | Prior to Prestashop yes After Prestashop the error showed up | Ajeet | 2014-08-05 | Have sent this error over multiple times.
2014-08-05 | Cannot create SO's this morning | Yes | Ajeet | 2014-08-05 | (3.25 hours)
2014-08-01 | Learned receiving was not receiving items into correct stock locations. Cricket tried to resolve - verify it is all correct now. |  |  | 2014-08-06 | Training done
2014-08-04 | Authorize.net charging $0.01 on declined transactions | Yes |  | 2014-08-06 | No longer happening
2014-08-04 | Training needed - how to receive against PO when not all goods are in the building |  |  | 2014-08-06
2014-08-04 | How to handle raw materials or packaging that is being returned to the supplier |  |  | 2014-08-06 | Return from Invoice
2014-08-04 | Invoice for Shelly with 4oz Herbal Calcium did not generate a Delivery Order | Yes |  | 2014-08-06 | Seems to be when creating an invoice without first creating an SO. Invoice won't allow you to cancel without first cancelling DO - however; it won't generate a DO. DO NOT CREATE INVOICES THIS WAY! Always create a SO, then create the Invoice from the SO.
2014-08-05 | Supplier Invoice - ability to edit Class, Discount Code and Description on Paid invoices. | Yes |  | 2014-08-06 | Fixed
2014-08-05 | Authorize.net is double charging again | Yes - just yesterday except for charging 1 penny on declined cards |  | 2014-08-06 | Not happening today
2014-08-05 | COGS account for July is 1.4 million ?? | ? | Sagar | 2014-08-06 | Issue with Spirulina received as grams instead of kilograms.
2014-08-05 | Training? Or fix? We still get Purchase Requisitions AND Quotes instead of just Purchase Requisitions | No |  | 2014-08-06 | Our setup was incorrect
2014-08-05 | Website wouldn't allow customer past entering email address - they had to call in to place their order over the phone | Yes |  | 2014-08-06 | Customer already had an account - it won't create another account for same email
2014-08-05 | Training to understand: When receiving, products hit what accounts? A/P and INV &/or COGS On customer invoice, products are hitting what accounts? Sales and COGS Also, on the supplier invoice-we chose cost of goods account for products, correct? The production location will determine where it is inventory? OR with real time, do we chose inventory account? I can make sense out of both ways so really need to bring clarity for myself if nothing else. Sorry. Delia had a cheat sheet from when Dheeraj was here on what accounts are being affected. Please double check with her and Dheeraj. It will make sense to you  | ? |  | 2014-08-06 | Training done
2014-08-06 | Lara, Ship1 and other Authenticator codes not working | Yes | Ajeet | 2014-08-06 | Corrected. Do not know cause of error yet.
2014-08-06 | How to correctly write a check to pay for a PO on items we have not yet received | ? |  | 2014-08-06 | Training done
2014-08-06 | Training - how best to substitute products in shipping - on DO, on Invoice - whatabout from Deliver Product instead of Deliver Order? |  |  | 2014-08-06 | Training done
2014-08-06 | How to fix when receive too much on a PO - if we say we got 10,395 but only really got 10,080 how do we fix it? |  | Sagar | 2014-08-06 | Training done
Week of July 28th | How to add raw materials and packaging items to invoices - will the Delivery Order know where to pull the stock from? | ? |  | 2014-08-06 | Training done
2014-08-01 | Not enough Clove to build MO | ? | Sandy & Ajeet | 2014-08-07 | Appears that Clove Capsules were in manufacturing during inventory - already built as capsules and counted as such. However; MO was not yet entered into system. Ajeet and Tracy fixed
2014-08-04 | Items in packages are doubled on Delivery Orders |  |  | 2014-08-07 | Cannot duplicate - seems to have been an issue with the packages being setup with the wrong number of items. Now that the packages are correct, the DO's are correct as well.
Since we started with Bista | Server is too slow - quote received and approved provided it causes no new problems | No | Saurav | 2014-08-11 | Upgraded
2014-08-12 | Ability to remove dropdown options we have typed in error? |  | Ajeet | 2014-08-12 | Said it is a browser history issue, clear that and it should go away. | Tracy need help
2014-08-11 | Authorize giving an error when invoice is over 30 lines |  | Sagar | 2014-08-13 | No fix. We will have to process the payment separate, not thru the invoice. I (Tracy) suggested we change the script to check the line count and anything greater than 29 lines the output submitted to API is 29. Anything 29 lines or less the output submitted to API is true line count.
2014-08-04 | QC, how to handle a MO when capsule fill is over what is in system has it is different each time (more or less), no scrapping as it was used to make product also if more or less -do we adjust capsule amount too. Reported again 8/11/14 |  | Sagar | 2014-08-13 | Update quantity to get capsule count correct and add raw material used.
2014-08-13 | Prestashop syncs back to ERP. Needs to stop changing descriptions! |  | Ajeet | 2014-08-13 | Actually some one create product at prestashop and then synchronize with openerp which is wrong process.As we already decided first we create product In OpenERP then sync from OpenERP to pretashop. Checking on how to correct when Description is changed
2014-08-14 | Need training on variant products that the size is the same but item code is different. Get an error that 2oz cannot be on there twice & need to know how best to add HC items. |  | Ajeet | 2014-08-14 | Checking on this - they have to have separate item numbers.
2014-07-23 | Femme Defense Pricing not correct | Yes | Ajeet | 2014-08-19 | Corrected with Ajeet - just needed to remove price from product template info tab
2014-08-06 | Sometimes when opening Chart of Accounts - Profit and Loss, we get all of the sub-accounts twice and other times only once. Why? |  | Ajeet | 2014-08-19 | Refresh the page
2014-08-08 | Receiving not able to receive a powder due to uom in grams 4567.2. Erp giving error that uom not allow 0.2 only 0.001. |  | Ajeet | 2014-08-19 | Appears to be fixed
Week of July 28th | Procurement locations do not match up with stock locations | ? | Ajeet | 2014-08-19 | We need to set this up. Locations were not yet created when reorder rules were setup. When locations were setup, reorder rules were not updated with correct procurement locations. Was finished last week while I was on vacation
2014-08-19 | PrestaShop server went down | Yes | Mark / Ken | 2014-08-19 | About an hour to fix
2014-08-20 | Error when clicking to view Deliveries on a product | Yes | Sagar | 2014-08-20 | Fixed in a matter of minutes
2014-08-19 | Found that we have two separate items for tamper bands used on 1,2, & 4oz bottles and two items for tamper bands used on 8 & 16oz bottles. | No | Tracy | 2014-08-20 | Verified my thoughts on how to fix this were correct. Added inventory of duplicate items together, updated that as the correct inventory on the item used in BOM's - added the "mm" measurement to item name to avoid confusion in the future - removed inventory from duplicate we would not be using and made it inactive.
2014-08-20 | PrestaShop server went down | Yes | Mark / Ken | 2014-08-20 | Down for about an hour - servers are being blocked as there is a new virus/hacking situation throughout the web, according to Ken
2014-08-20 | Pop-Up window to enter products on orders is no longer there. | Yes | Ajeet/Sagar/Saurav | 2014-08-20 | Fixed in an hour or less
2014-08-11 | Login, able to click refresh when asking for a secret code and opens ERP anyway |  | Sagar | 2014-08-21 | Finally duplicated - only happens if the system logs you out for inactivity, but won't work if you log yourself out
Mid July 2014 | Error when clicking to view Users | Yes | Ajeet | 2014-08-26 | In progress
2014-08-20 | Address is missing from List view of Customers | Yes |  | 2014-08-26
2014-08-20 | Wanda clicked the button to push the 1 ounce products she wanted to PrestaShop but they didn't show up | Yes |  | 2014-08-26 | Fixed
2014-08-20 | Packages are showing up as their own item awaiting availability on DO's - and apparently have been since July sometime. | Yes - I think it was working originally. |  | 2014-08-26 | Could be a settings issue or a code issue. Waiting to find out. Since some are awaiting availability since before our last inventory count we will need to re-verify the inventory before we mark them all as delivered. This was our fault. Someone keeps changing Packages from service items to stockable items. if they are listed as stockable they do not function properly and cause issues on the Delivery Orders.
2014-08-04 | OVP Items - are they in Finished Goods stock location? | ? |  | 2014-08-27 | We may have reviewed this earlier and I forgot to mark the worksheet so I double checked today, and yes they are in the right location
2014-08-04 | Formulas - what location are finished formulas going into | ? |  | 2014-08-27 | Production Formulas (again, may have reviewed earlier and forgot to mark the worksheet so I double checked today)
2014-08-27 | Prestashop orders for $0.00 won't pull into OpenERP. |  |  | 2014-08-28 | Not worth the expense
2014-08-27 | Training needed - how to update Inventory Loss if we put too much there on an inventory update |  |  | 2014-08-29 | Happens automatically
2014-09-02 | Acess denied when trying to unreconcile or cancel an invoice | Yes |  | 2014-09-02 | Had this issue last week and it was fixed. Seems to have reappeared this week. Fixed in a few minutes. Apparently the sales team needs access rights to the cash flow module to be able to change an invoice. I have asked if this should be setup that way.
2014-08-20 | Sherie cannot save her changes to the work summary in a project | ? |  | 2014-09-04 | Tested 9/2/14 - still not working - sent new screen shot Have to create product for Labor and assign it to employees for them to save work summary information in a project.
2014-08-28 | Training needed - how to see where the information is coming from that is changing the Virtual Stock of an item. If you have one MO open that wants 2688 ounces, and stock by location says you have 2688 ounces, then why is Virtual Stock -652 ounces. What else is wanting that item? |  |  | 2014-09-08 | Because the inventory was changed before an MO was finished
2014-09-02 | Error trying to deliver DO OUT/15525 | Yes |  | 2014-09-09 | Website connector is no longer connecting between Prestashop and OpenERP due to changes on the server with our security certificate.
2014-09-02 | OpenERP won't register Prestashop Payments today | Yes |  | 2014-09-09 | Website connector is no longer connecting between Prestashop and OpenERP due to changes on the server with our security certificate.
2014-09-01 | PrestaShop and Website down | Yes | Mark/Ken | 2014-09-09 | FatCat updating server
2014-09-03 | PrestaShop and Website down | Yes | Mark/Ken | 2014-09-09 | Per Mark: i've contacted Host... i do know that last couple of days the host has been updating to faster, better servers
2014-09-02 | Error while registering a payment | Yes |  | 2014-09-09 | Lara sent screenshot Had to do with issue of Prestashop and OpenERP not communicating because Ken moved Prestashop to a new server and something with the IP didn't move correctly and caused issues.
2014-09-09 | How to correct DO's that have a package item that is not in stock so they can moved to "delivered" status. |  | Ajeet | 2014-09-18 | Done
2014-08-18 | PrestaShop - some products are going under Freight Revenue instead of correct account | ? | Ajeet and Imran | 2014-09-19 | This seems to only be products that Prestashop has created in OpenERP Prestashop disconnected from OpenERP. We will be moving to Magento
2014-08-29 | Need a way to enter deviations | No | Ajeet | 2014-09-19 | Getting quote
Week of July 28th | PrestaShop is creating products in OpenERP Which product do we keep? OpenERP or PrestaShop Created. How do we stop it from happening again? | Seemed to be | Ajeet and Imran | 2014-09-23 | I (Tracy) manually marked inactive all duplicate products, had Ajeet fix the pricing on those that needed it fixed and it should not happen again because Prestashop is now disconnected from OpenERP
2014-08-19 | At least 15 MO's and possibly more that are not recognizing they have enough of something in inventory to be built. | n/a | Ajeet and Tracy | 2014-09-23 | Researching each one individually. Solved 3 or 4 on 8/19/14. Solved another few on 8/20/14. Should all be fixed and should not see the problem continuing after fiscal year end inventory updates This is an ongoing process currently (8/27/14) - I am finding many that are errors in counting inventory (both in whether or not we counted everything, as well as errors regarding what phase something was in on MO's vs what phase it was actually in) also finding errors in setup of units of measure and how they calculate, errors in what location items are received into, etc... The majority of these issues are user error.
2014-08-27 | Found we have inventory counts in multiple locations on some products. When they are received into the wrong location, and inventory is done, the script puts the inventory into the correct location but does not remove it from the incorrect location. When the scheduler runs, it adds up the inventory in all locations so it doesn't know you are almost out of something because it still has quantity in the wrong location. |  | Ajeet | 2014-09-23 | I need to manually go through every product and look at the Stock by Location information and make sure it is in the correct location and 0 out that which is in the wrong location. - We had Ajeet do this with a script when inventory was updated for end of fiscal year
2014-08-29 | Button to remove from "to be consumed" removes everything for that item including what was consumed already instead of just the amount on the "to be consumed" side. If you click the line item and open it up the Cancel Transfer button works correctly. Either remove the other button or make it function the same way as the cancel transfer button inside the window | ? | Ajeet | 2014-09-23 | Button was removed
2014-09-10 | Inventory not updating the stock by location numbers when items are built - why? | We thought it was | Ajeet | 2014-09-23 | Found that stock wasn't being updated because the MO's were created before locations were created so the MO's were affecting the wrong stock locations.
2014-08-20 | Sent over 13 SOP's for Review | n/a | Ajeet | 2014-09-24
2014-08-29 | New endecia account not working | No - new account number | Ajeet | 2014-09-25 | Had to do with the password not being permanent and some settings regarding having money in the account.
2014-09-23 | ERROR: Unit of measure rounding does not allow you to ship "160.0 ounce (oz)", only rounding of "0.0 ounce (oz)" is accepted by the Unit of Measure. This particular time it is with cornsilk. We have this error happen regularly on different items, each time we change the rounding to allow something to be received it causes the rounding for other items to not work. Why? How do we permanently fix the rounding so that we don't have to change it regularly to be able to receive or utilize products? | Has been problematic all along | Ajeet | 2014-09-29 | Ajeet found a fix that seems to be working
2014-10-02 | Yeast X Package is once again a stockable item instead of a service item. | Yes | Ajeet | 2014-10-02 | Corrected the issue, however; not entirely positive of the cause. Looking at the first orders to have the package as a line item I am guessing it is a Prestashop leftover. Prestashop was disconnected from OpenERP on 9/19 and this appears to have happened on 9/18. If it happens again we will know for sure it isn't Prestashop. If it doesn't happen again then we know for sure it was Prestashop.
2014-10-02 | Spirulina mysteriously changed from 99.95kg to over 22,700 kg for the inventory value. Why? | Not that I'm aware of | Ajeet | 2014-10-06 | After updating mmherbstest environment to latest version of db we found that our changes to correct the UofM on kg caused the change to the inventory value. Changes to UofM did not used to change inventory value, but now do.
2014-09-02 | Shipping being calculated incorrectly - either Endicia API issue or OpenERP issue. It is off by one ounce. | Yes | Ajeet | 2014-10-06
2014-08-05 | Remove all other login methods aside from google authenticator. Remove all excess users (Gascho's, Gina Madrid, Robert Ong, etc..) that are not needed and their existence is not understood in the first place. | No | Ajeet | 8/19-20/14 | We have been asking for excess user removal for quite some time. We are now ready for all other login methods to be removed.
2014-08-05 | When 2 people are labeling packages in shipping at the same time the system will update the default package size to the package the other person labeled | No - has always existed |  |  | Requested quote - not high priority
2014-08-05 | Payment processing error | Yes | Dheeraj / Ajeet |  | When using Accounting > Customer Payments we get a warning that an entry is already reconciled
2014-08-05 | Training needed - How to correctly setup separate ship to addresses in the system - Via "Contacts" or via checkbox on Invoice for "alternate delivery address" ? | contacts was at one point.
2014-08-05 | Training needed - How to track number of new customers? | ?
2014-08-05 | Training needed or Fix - not sure which - Project Stages are not staying in order when viewed by other users - only by the user who created the project. | ?
2014-08-05 | Training Needed - How to handle items that are drop shipped from another location. Do we force reservation? Do we receive the items into inventory on the supplier invoice? Are they service items instead? If so - how to track the number sold in a given time period? | ? |  |  | Quote requested
2014-08-06 | CC Declined in OpenERP yet entered into Authorize.net website processes fine - why? Reported again 8/11/14 | ? | Ajeet, Sagar and OpenERP |  | What is decline message - what is customers ID This appears to have something to do with the issue that OpenERP is not designed to allow more than one person to process credit card payments at one time.
2014-08-15 | Didn’t hear from Ajeet or Sagar. Sent Ajeet skype at 7:24am...Hello Ajeet, Is there a way to designate an account to a supplier. For example, Mtn Rose Herbs will most likely always be a COGS-Bulk Herbs? Or how best to set up expense accounts to be the default instead of the amorization account being the default? |  | Ajeet |  | Checking on this Create items for expenses like "production supplies" "office supplies" etc… - need new category?
2014-08-20 | Payment error - claiming Duplicate Payment when only processed once | Yes | Ajeet and OpenERP
2014-08-20 | Training needed - how to enter more than one invoice on one PO | No - system not designed for this |  |  | Quote needed on this
2014-08-28 | learned the COGS account is incorrectly affected. Getting quote for costing module and meeting with Matt Lynn tomorrow to discuss what should be happening. The system uses the dollar amount off the product form view for touching COGS during Receiving, and the dollar amount off the Supplier Invoice for touching COGS during invoicing/payment - these do not zero each other out.
2014-08-29 | Update button inside MO's doesn't let you choose unit of measure, it just automatically uses default UofM for item which creates issues in "to be consumed" side | No |  |  | Getting quote
2014-10-06 | PO 286 has incorrect value in Description for ZMYR02 - it has ZMYR01 instead of ZMYR02. I cannot edit the PO. Sent to developers to see how to fix.